## HPDTAS
0
MOSH HPD TAS Adoption Programme Monitor for the Adoption of the HPD TAS leading practice - April 2013
COPA | Mining House | Number | Name of Mine/ Shaft | Company | Name of Manager | Name of Project Leader | E-mail Address of Project Leader | Telephone Number | Do you have a FOG Risk associated with nets with bolts? | Do you have FOG Risk Controls in place | Do you have a Procedure on the application of Bolts with Nets | Is your FOG related LTIFR<0,05 | Have you considered the Adoption of the Leading Practice on Nets with Bolts | Yes, we want to Adopt the Leading Practice on Nets with Bolts | No, we do not want to Adopt the Leading Practice on Nets with Bolts | Setting up Multi disciplinary Adoption Teams | Induction of the Adoption Team (s) | Agree on the Implementation Plan | Identify the interviews & Interviews | Train the Interviewers | Mental Model Interviews | Leadership Behaviour Plan | Behaviour Communication Plan | Risk Assessment | Training Lesson Plans | Management Review Process | Roll-out plan in place | Challenges | Highlights | Number of People covered | COPA Participation
| ARM | 1 | Two Rivers | Harmony |  | Rusiano Tsoka | rusiano.tsoka@harmony.co.za | 829271018 | y | Y | Y | Y | Y | [8 empty] | NS | NS | NS | NS | NS | NS |  | Cooperative and high level involvement | 3486 | EL
|  | 2 | Nkomati | [18 empty] | NS | NS | NS | NS | NS | NS | Compare with action plan | Cooperative and high level involvement | 3128
|  | 3 | Modikwa | [13 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS |  |  | ?
|  | 4 |  | Anglo Gold Ashanti |  | Thembinkosi Madondo | mmadondo@anglogoldashanti.com | 187006279 | y | y | y | y | y
| EXXARRO | 1 | Arnot | Anglo Gold Ashanti | Francois Naude |  | fnaude@anglogoldashanti.com | 713635097 | y | y | y | y | y |  |  | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Occ hygienist still going to sell to their GM's | Pro-activeness from Group SHEQ | ?
|  | 2 | Matla | Harmony |  | Marius Van der Merwe | marius.vandermerwe@harmony.co.za | 0723684289/0574524445 | y | y | y | y | y |  |  | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Occ hygienist still going to sell to their GM's | Pro-activeness from Group SHEQ | ?
|  | 3 | Groote Geluk | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Occ hygienist still going to sell to their GM's | Pro-activeness from Group SHEQ | ?
4
|  | 5 |  | Harmony | Rudi Phillis | Tienie Landman | Tienie.Landman@Harmony.co.za | 579167111 | y | y | y | y | y
| IMPALA | 1 | Shaft 1 | Xstrata Alloys |  | Phil Garner | pgarner@xstrata.co.za | 829219441 | y | y | y | y | y |  |  | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership | Training center is exited with material | 4565
|  | 2 | Shaft 2 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 689
|  | 3 | Shaft 4 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 1755
|  | 4 | Shaft 5 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 480
|  | 5 | Shaft 6 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 1195
|  | 7 | Shaft 7A | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 1419
|  | 8 | Shaft8 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 980
|  | 9 | Shaft9 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 2126
|  | 10 | Shaft10 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 3181
|  | 11 | Shaft11 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 6966
|  | 12 | Shaft 11C | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 32
|  | 13 | Shaft12 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 3746
|  | 14 | Shaft 14 | Anglo Gold Ashanti | Randel Rademan |  | crrademann@anglogoldashanti.com | 187005450 | y | y | y | y | y |  |  | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 4803
|  | 15 | Shaft 16 | Harmony |  | Velaphi Waganda | velaphi.waganda@harmony.co.za | 579074114 | y | y | y | y | y |  |  | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 1046
|  | 16 | Shaft 17 | Harmony |  | Warren Freeman | Warren.Freeman@harmony.co.za | 847016876 | y | y | y | y | y |  |  | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 427
|  | 17 | Shaft 20 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 2677
|  | 18 | Shaft7A | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 1244
|  | 19 | Shaft EF | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 759
|  | 20 | Processing | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 641
|  | 21 | SMLT | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 637
|  | 22 | Tailings | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 237
|  | 23 | Toll | Anglo Gold Ashanti | Andre van Jaarsveld | Danny Davis | ddavies@anglogoldashanti.com | 187008963 | y | y | y | y | y |  |  | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 8
|  | 24 | UG2 | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 196
|  | 25 | General | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 336
|  | 26 | Laboratories | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 48
|  | 27 | Minpro | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 1469
|  | 28 | Medical Services | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 108
|  | 29 | Services | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 4955
|  | 30 | Opencast | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | Still verifying union membership |  | 207
|  | 31 | Grand Total | [25 empty] | Grand Total | 46932
32
| NORTHAM | 1 | Zondereinde Platinum | Impala | Mathias Sithole |  | Mathias.sithole@implats.co.za | 829431572 | y | y | y | y | y | [5 empty] | IP | IP | IP | NS | NS | NS | NS | NS | NS | Active participation from unions | Good cooperation | 9116
|  | 2 | Grand Total | [25 empty] | Grand Total
|  | 3 |  | Harmony | Theo Keyter |  | Theo.Keyter@harmony.co.za | 187829152 | y | y | y | y | y
|  | 4 |  | Harmony | Pieter Fourie | Pieter Fourie | Pieter.Fourie@harmony.co.za | 829403283 | y | y | y | y | y
| XSTRATA - ALLOYS |  | Eastern Chrome Mines
|  | 1 | Thorncliffe | [12 empty] | IP | IP | IP |  |  | NS | NS | NS | NS | NS | NS | NS |  | High level production people participation | 946
|  | 2 | Magareng | [12 empty] | IP | IP | IP |  |  | NS | NS | NS | NS | NS | NS | NS |  | High level production people participation | 910
|  | 3 | Helena | [12 empty] | IP | IP | IP |  |  | NS | NS | NS | NS | NS | NS | NS |  | High level production people participation | 941
|  | 4 | UG 2 | [12 empty] | IP | IP | IP |  |  | NS | NS | NS | NS | NS | NS | NS |  | High level production people participation | 17
|  | 5 | Shared Services | [12 empty] | IP | IP | IP |  |  | NS | NS | NS | NS | NS | NS | NS |  | High level production people participation | 340
|  |  | Grand Total | [25 empty] | Grand Total | 3163
Western Chrome mines
|  | 1 | Rietvlei | [16 empty] | IP | IP | NS | NS | NS | NS | NS | NS |  | Excellent feedback on progress against project plan | 49
|  | 2 | Kroondal | [16 empty] | IP | IP | NS | NS | NS | NS | NS | NS |  | Excellent feedback on progress against project plan | 969
|  | 3 | Waterval | [16 empty] | IP | IP | NS | NS | NS | NS | NS | NS |  | Excellent feedback on progress against project plan | 745
|  | 4 | Horizon | [16 empty] | IP | IP | NS | NS | NS | NS | NS | NS |  | Excellent feedback on progress against project plan | 563
|  | 5 | UG 2 | [16 empty] | IP | IP | NS | NS | NS | NS | NS | NS |  | Excellent feedback on progress against project plan | 334
|  |  | Grand Total | [25 empty] | Grand Total | 2660
| SASOL | 1 | Syferfontein | [24 empty] | Too long lead times |  | ?
|  | 2 | Brandvlei | [24 empty] | Too long lead times |  | ?
|  | 3 | Secunda | [24 empty] | Too long lead times |  | ?
| HARMONY | 1
2
3
4
6
7
| XSTRATA - PLATINUM |  | Eastern Platinum Mines
|  | 1 | Mototolo Borwa | [17 empty] | NS | NS | NS | NS | NS | NS | NS |  |  | 842
|  | 2 | Mototolo Lebowa | [17 empty] | NS | NS | NS | NS | NS | NS | NS |  |  | 1321
|  | 3 | Grand Total | [25 empty] | Grand Total | 2163
Western Platinum mines
|  | 1 | Eland | [12 empty] | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | NS | To establish an internal team |  | ?
2
3
Note on R7: JDeBeer01: First meeting on 26th April 2013
Note on E9: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on E10: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on E11: JDeBeer01: First meeting was not with the mine adoption team, but with Occ hygienist
Note on U46: JDeBeer01: Still finishing ID of Interviewees
Note on W58: JDeBeer01: Expect to be finished by end April 2013. overall completion is 50% to date
Note on W59: JDeBeer01: Expect to be finished by end April 2013. overall completion is 50% to date
Note on W60: JDeBeer01: Expect to be finished by end April 2013. overall completion is 50% to date
Note on W61: JDeBeer01: Expect to be finished by end April 2013. overall completion is 50% to date
Note on W62: JDeBeer01: Expect to be finished by end April 2013. overall completion is 50% to date
Note on E64: JDeBeer01: Team establishment will take place on 23 April 2013
Note on E65: JDeBeer01: Team establishment will take place on 23 April 2013
Note on E66: JDeBeer01: Team establishment will take place on 23 April 2013